6.1. 活動概要 Summary of activity

| 活動 | 內容 | 詳情 |  | 目標對象 | 直接參與人數 | 間接參與人數 |
| --- | --- | --- | --- | --- | --- | --- |
| Project Launch and Whole-School Talk | A school-wide talk will launch the programme by introducing key biodiversity concepts and their relevance to everyday life in Hong Kong. Led by a conservation expert, the session uses real-world examples to deepen understanding, raise ecological awareness, and inspire action. It provides a strong foundation for further exploration by Form 2 and 3 students. | 日期及時間 | Early Jan 1:50-2:50 | Form 1 to Form 6 Students | 710 | 775 (710 + 65 teachers) |
|  |  | 每節時間 | 1.5 |  |  |  |
|  |  | 總節數 | 1 |  |  |  |
|  |  | 總時數 | 1.5 |  |  |  |
|  |  | 地點 | School Hall |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| 1a) Form 2 HKBM Visit | All Form 2 students will visit the Hong Kong Biodiversity Museum to explore preserved specimens and learn basic classification systems. In small groups, they will take part in guided observations and discussions, focusing on how species are grouped and identifying key features used in classification, such as body structure, symmetry, and habitat. | 日期及時間 | Mid-Feb 13/2/2026 13:50-15:50 | Form 2 Students (4 classes) | 132 | 132 |
|  |  | 每節時間 | 2 |  |  |  |
|  |  | 總節數 | 4 |  |  |  |
|  |  | 總時數 | 8 |  |  |  |
|  |  | 地點 | Hong Kong Biodiversity Museum |  |  |  |
|  |  | 地區 | Central and Western District |  |  |  |
| 1b) Field Trip to Taipo Kau with a photo-taking task | Students will visit Tai Po Kau Nature Reserve as part of the EcoVerse programme to explore Hong Kong’s forest biodiversity. Using the iNaturalist app, students will photograph and identify 3–5 local species such as plants, insects, or fungi along forest trails. Outstanding photos will be featured in the Photo Showcase, promoting student creativity and environmental awareness through real-world ecological exploration. | 日期及時間 | Mid March 13:50-15:50 | Form 2 Students (4 classes) | 132 | 132 |
|  |  | 每節時間 | 2 |  |  |  |
|  |  | 總節數 | 4 |  |  |  |
|  |  | 總時數 | 8 |  |  |  |
|  |  | 地點 | Taipo Kau |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| 1c) Form 2 Photography Contest | Form 2 students are invited to participate in the “Nature in Our Backyard” Photography Contest by submitting a photo taken during their field trip. Shortlisted entries will be open to school-wide voting during lunchtime (one hour per day), and the winning photos will be featured on Open Day, with 2 hours counted as preparation | 日期及時間 | Late March | Submission: Form 2 Students Voting: Form 1 to Form 5 Students | 590 | 650 (590 + 60 teachers) |
|  |  | 每節時間 | 1 |  |  |  |
|  |  | 總節數 | 1 |  |  |  |
|  |  | 總時數 | 1 |  |  |  |
|  |  | 地點 | School |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| 1d) Form 2 AI Teachable Machine - identification | Students will participate in a hands-on AI activity to deepen their understanding of biodiversity and technology. Using photos taken during their Tai Po Kau Nature Reserve field trip, students will upload and train a machine learning model. They will categorize and label 3–5 local species—such as plants, insects, or fungi—to teach the AI how to recognize them. This activity encourages students to engage critically with ecological data and gain foundational knowledge in artificial intelligence. Selected student models or screenshots may be highlighted in an AI Showcase. | 日期及時間 | Mid-April | Form 2 Students | 132 | 132 |
|  |  | 每節時間 | 2 |  |  |  |
|  |  | 總節數 | 4 |  |  |  |
|  |  | 總時數 | 8 |  |  |  |
|  |  | 地點 | School |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| 2a) Form 3 Classification Lesson | Form 3 students will explore biological classification by creating dichotomous keys based on local marine species, including examples from the coral tank. This interactive activity enhances their observation and logical thinking skills through practical, hands-on learning. | 日期及時間 | Mid-Feb | Form 3 Students | 132 | 132 |
|  |  | 每節時間 | 40 mins |  |  |  |
|  |  | 總節數 | 4 |  |  |  |
|  |  | 總時數 | 2 hrs 40 mins |  |  |  |
|  |  | 地點 | Classroom |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| 2b) Form 3 SWIMS Visit – Intertidal Exploration | Form 3 students will conduct an intertidal field survey using transect lines and quadrats to collect real-world biodiversity data. Through this hands-on activity, they will practice key ecological field techniques and develop observation and data recording skills in a natural coastal environment. | 日期及時間 | Mid-March 8:00-12:00 | Form 3 Students | 132 | 132 |
|  |  | 每節時間 | 4 |  |  |  |
|  |  | 總節數 | 4 |  |  |  |
|  |  | 總時數 | 16 |  |  |  |
|  |  | 地點 | Swire Institute of Marine Science (SWIMS) |  |  |  |
|  |  | 地區 | Southern District |  |  |  |
| 2c) Form 3 Biostatistics Workshop | Form 3 students will join a data analysis workshop using findings from the ARMS field visit. With guidance and GenAI tools, they will organize, analyze, and present biodiversity data through charts and graphs—practising classification and exploring correlations between species. This session builds skills in scientific thinking and digital literacy. | 日期及時間 | Late March 13:30-14:30 | Form 3 Students | 132 | 132 |
|  |  | 每節時間 | 2 |  |  |  |
|  |  | 總節數 | 4 |  |  |  |
|  |  | 總時數 | 8 |  |  |  |
|  |  | 地點 | School Computer Room / Classrooms |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| 2d) Form 3 Design Thinking – Infographic Creation | Form 3 students will apply design thinking to transform their learning into impactful infographics. Drawing especially from their biostatistics workshop findings, they will creatively summarize data and conservation messages—enhancing both scientific communication and visual storytelling skills. | 日期及時間 | Mid-April | Form 3 Students | 132 | 132 |
|  |  | 每節時間 | 40 mins |  |  |  |
|  |  | 總節數 | 4 |  |  |  |
|  |  | 總時數 | 2 hrs 40 mins |  |  |  |
|  |  | 地點 | School Computer Room / Classrooms |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| Whole-School Open Day Showcase | The Whole-School Open Day Showcase presents Form 2 student photography and Form 3 marine biodiversity infographics. Through interactive booths, visual displays, and student-led activities, participants share their discoveries with peers, teachers, and families—promoting biodiversity awareness while celebrating creativity, observation, and hands-on ecological learning across the school community. | 日期及時間 | Late May 10:00-16:00 | Whole school + families | 710 | 900 |
|  |  | 每節時間 | 6 |  |  |  |
|  |  | 總節數 | 1 |  |  |  |
|  |  | 總時數 | 6 |  |  |  |
|  |  | 地點 | School |  |  |  |
|  |  | 地區 | Taipo District |  |  |  |
| 總參與人數 |  |  |  |  | 2934 | 3249 |